## Risk_Log
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation | Risk Owner | Open/Closed
R1 | 2022-06-01 | Financial Loss | Acqusistion of Duke Realty and further inability to derive profits | Huge financial losses | Leading to closure of the deal | 5 | 8 | 40 | H | Proper utiliztion of new technology to gain profits | CFO | Open
R2 | 2022-06-05 | Operations | Integration of Duke Realty's logistic solutions with Prologis's existing technology | Delay in product integration | Financial loss and loss of customers | 7 | 6 | 42 | M | Timely integration | COO | Open
R3 | 2022-06-07 | Competition | High competition in the market with existing real-estate leaders | improved products and fierce battle for market share | Loss of market share | 9 | 9 | 81 | H | Better product releases or loss of market share due to low innovation | CTO | Open
R4 | 2022-06-10 | Reputation | Due to acquisition of Duke Realty | If integration fails | Loss of customers | 5 | 6 | 30 | H | Better and timely integration | COO | Open
R5 | 2022-06-12 | Technical | Failure in integration of new logistic solutions and technology | Loss of trust and reputation | Loss of potential and existing customer base | 7 | 4 | 28 | M | Better and timely integration | CTO | Open
R6 | 2022-06-13 | Legal | Error in paper works | Delayed acquisition | Delay in building new acquired company | 3 | 2 | 6 | L | Diligent Paper work | Lawyers | closed

## Risk_HeatMap
Risk ID | Description | Likelihood/Probability |  |  | Impact
R1 | Financial Loss | 5 |  |  | 8
R2 | Operations | 7 |  |  | 6
R3 | Competition | 9 |  |  | 9
R4 | Reputation | 5 |  |  | 6
R5 | Technical | 7 |  |  | 4
R6 | Legal | 3 |  |  | 2
|  |  | Priority | Color | Action
|  |  | Low |  | Make Do
|  |  | Medium |  | Monitor/Manage
|  |  | High |  | Mitigate