## Sheet1
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation | Risk Owner | Open/Closed
1 | 2022-06-01 | Increased competition in the Real Estate Investment Management, logistics solutions and services | Prologis acquisition of Duke Realty for it's premium industrial properties and logistics solutions. | Fierce competition with other companies operating in the similar space | This may lead to development of better products and technology or being wiped out of market | 85% | 90% | 90% | H | Keep innovating and building technically sound products for avoiding losing out of market share | Product Manager | Open
2 | 2022-06-10 | Time consuming process of integration | Difficulty in integrating Prologis Logistics solutions with Duke Realty's existing technology | Increase in cost and extension of project timelines | delayed delivery of projects | 65% | 87% | 85% | M | Early detection of bugs and refining existing products to match up with the new technology | Senior Software Engineer | Closed
3 | 2022-06-13 | Increase in technical and information security vulnerabilities | Legal and contractual obligations | Leakage of secret information - trade, tarriff rates etc. | Losing trade secrets | 40% | 90% | 95% | H | Hire the best legal team to sail through the acquisition smoothly. | CTO and Head of Legal Team | Open